## Gantt Chart
GANTT CHART
PROJECT TITLE |  | CAIRN CONGREGATION |  |  |  |  | COMPANY NAME | [6 empty] | DECARLO DEVELOPERS
PROJECT MANAGER |  | DANIEL DECARLO |  |  |  |  | DATE | [6 empty] | 2020-02-12
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Planning and Design
1.1 | Develop Project Quote | Daniel DeCarlo | 2020-01-29 | 2020-02-05 | 6 | 100% | bar: WEEK 1 F to WEEK 2 T
1.1.1 | Create Use Case Diagram | Daniel DeCarlo | 2020-02-06 | 2020-02-12 | 6 | 100% | bar: WEEK 2 W
1.2 | Create Site Map | Daniel DeCarlo | 2020-02-06 | 2020-02-12 | 6 | 100% | bar: WEEK 2 W to WEEK 3 W
1.3 | Revise Site Maps and Use Cases | Daniel DeCarlo | 2020-02-13 | 2020-02-19 | 6 | 100% | bar: WEEK 2 R to WEEK 3 R
1.4 | Create Wire Frames | Daniel DeCarlo | 2020-02-13 | 2020-02-19 | 6 | 100% | bar: WEEK 3 M to WEEK 3 R
2 | Coding Front-End
2.1 | Create Log In Page | Daniel DeCarlo | 2018-03-24 | 2018-03-28 | 4 | 100% | bar: WEEK 4 M to WEEK 4 R
2.2 | Create Navigation Bar | Daniel DeCarlo | 2018-03-29 | 2018-04-02 | 3 | 100% | bar: WEEK 4 F to WEEK 5 F
2.3 | Style Site | Daniel DeCarlo |  |  | 0 | 15%
2.4 | Style Home Page With Events | Daniel DeCarlo |  |  | 0 | 0%
2.5 | Responsive (Optional) | Daniel DeCarlo
3 | Coding Back-End
3.1 | Create Database for Log In | Daniel DeCarlo |  |  | 0 | 100% | bar: WEEK 4 F to WEEK 5 W
3.2 | Create Profile Table and connect to Front End | Daniel DeCarlo |  |  | 0 | 50%
3.2.1 | Search For Other Alumni | Daniel DeCarlo |  |  | 0 | 100% | bar: WEEK 5 R to WEEK 6 T
3.2.2 | Update Profile Information | Daniel DeCarlo |  |  | 0 | 0%
3.3 | Admin Access | Daniel DeCarlo |  |  | 0 | 0%
4 | Post-Development
4.1 | Testing | Daniel DeCarlo |  |  | 0 | 0%
4.2 | Implementaton | Daniel DeCarlo |  |  | 0 | 0%
4.3 | Maintenance | Daniel DeCarlo |  |  | 0 | 0%
4.4 | Planning | Daniel DeCarlo |  |  | 0 | 0%